## cogan spray
NATL invasives: cogon grass
sprayed in 2008
TJW in charge through 26 Jul 06; Kevin Ratkus in charge from then until 2 Nov 07.
Robert Guggenheim put in charge 6 May 08.
RG turned over to Lary Reeves in late summer of 2010.
CG1 | retention pond for Surge Area mini-warehouses
2007-06-08 | sprayed Glypro on > 60 small patches
2007-07-27 | sprayed Glypro on 32 small patches
2007-09-07 | sprayed Glypro on 51 small patches
2007-11-02 | sprayed Glypro on > 60 small patches
2008-05-22 | Patches found
2008-06-19 | sprayed Glyphosate on 25 patches
2008-11-12 | sprayed Glyphosate on 57 plants
2008-12-15 | root-treated with Garlon on 54 plants (most in patches), flagged w/ red tape
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes/verified TJW
2009-06-26 | 7pink=1%Habitat+.25%Surfactant/7blue=.25%Habitat+.25%Surfactant/7red=2%Habitat.25%Surfactant
extended from experiment in CG17, all other cogan-sprayed Glyphosate on 28 plants, west of exp.
2009-06-29 | sprayed flagged areas
2009-07-13 | Glyphosate-sprayed plants are all dead/Red flagged-in shade yellowed, some small dead, dry/Blue-in
shade little yellowed, dry-in sun yellowed, dry/Pink-in shade dry, some small dead-in sun yellowed, dry
2009-07-29 | All concentrations are about 1/2 dead (all flagged areas)
2009-08-03 | Pulled 3 small plants by hand next to shed
2009-08-06 | Blue flags are still alive (barely). Pink are very yellowed and some dead in sun. Red are mostly dead.
2009-08-25 | All were found dead, except questionable:2 pink, and 2 blue.
2009-09-17 | sprayed 23 plants w/1%imazapyr;some Nof storage shed,some in woods inS&across fence in Swoods.
2009-10-20 | sprayed 20 withered/6 viable plants with 1% imazapyr.
2009-12-02 | sprayed 30 plants with 1% imazapyr, ~1/2 withered.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-02 | sprayed 8 plants with 1% imazapyr.
2010-07-06 | none found.
2010-08-05 | found plant in SW under brush near flags
2010-08-20 | tw found and sprayed with 1% amazapyr 1 plant ca 1.5m s. or w. end of n fence of mini-warehouses
CG2 | at SE corner of corral fence on either side of junction of E Trail and N Trail
2007-06-15 | sprayed Glypro on 12 small patches
2007-07-27 | sprayed Glypro on 1 small patches
2007-09-07 | sprayed Glypro on 2 small patches
2007-11-02 | no regrowth
2008-06-19 | no regrowth
2008-12-02 | 7 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2008-12-16 | 0 found on NE, sprayed Glyphosate on 8 new plants in SW
2009-06-01 | none found, pulled sample up to inspect, has deep purple base & no rhizomes
2009-07-22 | none found
2009-07-29 | sprayed 5 w/ glyphosate
2009-09-21 | sprayed 81 plants with 1% imazapyr.
2009-10-20 | sprayed 32 withered plants with 1% imazapyr.
2009-12-02 | sprayed 8 plants with 1% imazapyr, very withered.
2010-06-01 | none found.
2010-07-06 | none found.
*CG4 | N edge of Plot A (Experimental Plot)
2007-06-15 | Exp. started: sprayed Glypro on > 50 small patches on W side / No treatment on E side
2007-07-27 | sprayed Glypro on 27 small patches on W side / No treatment on E side
2007-09-07 | sprayed Glypro on 12 small patches on W side / No treatment on E side
2007-11-02 | sprayed Glypro on 9 small patches / Extensive growth > 60 on E side
2008-05-06 | no growth in W/ patches found in E
2008-06-19 | sprayed Glyphosate on 7W/12E patches
2008-11-10 | W-flagged orange,Garlon on 8 patches (3/1/5/10/18/8/1/10) / E-flagged blue,Glyphosate on 16 plants
2008-12-15 | W-flagged with red tape,root-treated with Garlon on 20 new plants
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes/verified TJW
2009-06-26 | 8pink=1%Habitat+.25%Surfactant/8blue=.25%Habitat+.25%Surfactant/8red=2%Habitat.25%Surfactant
2009-06-29 | sprayed flagged areas
2009-08-25 | All were found dead, except questionable:3 pink, 1 red, and 3 blue w/1 sprout next to a blue.
2009-09-21 | sprayed 39 plants with 1% imazapyr.
2009-10-20 | sprayed 16 withered plants with 1% imazapyr.
2009-12-02 | none found.
2010-06-02 | sprayed 3 plants with 1% imazapyr.
2010-07-06 | none found.
**CG6 | NW corner of Plot A and NE corner of nPAP
2007-06-15 | sprayed Glypro on 2 small patches
2007-07-27 | no regrowth found
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-16 | sprayed Glyphosate on 27 plants
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes
2009-07-22 | none found (johnson)
2009-09-21 | sprayed 32 plants with 1% imazapyr.
2009-10-20 | sprayed 11 withered plants with 1% imazapyr.
2009-12-02 | none found.
2010-06-02 | sprayed ~30 plants with 1% imazapyr (~3L).
2010-07-06 | none found.
CG7 | Plot A, along fire lane near its N end
2007-06-15 | sprayed Glypro on > 50 small patches (S of self-guided trail, really expansion of CG 4)
2007-07-27 | sprayed Glypro on 1 small patch W / sprayed Glypro-17 small patches on E(S of self guide trail)
2007-09-07 | no regrowth W / sprayed Glypro on 34 small patches on E (S of self guide trail)
2007-11-02 | no regrowth W / sprayed Glypro on 20 small patches on E (S of self guide trail)
2008-05-06 | addition of CG37 as separate area and sprayed 15 patches in CG37
2008-05-22 | Patches found
2008-06-19 | sprayed Glyphosate on 1 patch
2008-11-12 | sprayed Glyphosate on 2 patches
2008-12-16 | sprayed Glyphosate on 16 plants
2009-06-01 | none found
2009-07-22 | none found
2009-09-21 | none found
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-02 | none found.
2010-07-06 | none found.
**CG8 | Plot A, along fire lane between CG7 and west end of Old-field Trail
2007-06-15 | sprayed Glypro on 3 small patches
2007-07-27 | sprayed Glypro on 4 small patches
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-16 | sprayed Glyphosate on 13 plants
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes
2009-06-29 | None Found
2009-07-22 | none found
2009-09-21 | none found
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-02 | none found.
2010-07-06 | none found.
CG10 | Plot A, near center and eastward
2007-06-15 | sprayed Glypro on > 50 small patches (expansion north)
2007-07-27 | sprayed Glypro on 15 small patches
2007-09-07 | sprayed Glypro on 28 small patches
2007-11-02 | sprayed Glypro on 12 small patches
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-16 | sprayed Glyphosate on 30 plants near firelane(on E), sprayed 5.5 gal. on rest of CG10 (100 +/-)
2009-06-01 | Found among many grasses, pulled sample up to inspect, has long rhizomes
2009-06-29 | sprayed Glyphosate on 21 plants
2009-09-21 | sprayed 36 plants with 1% imazapyr.
2009-10-20 | sprayed 36 withered/37 viable plants with 1% imazapyr.
2009-12-02 | sprayed 36 plants with 1% imazapyr, mostly withered.
2010-06-02 | sprayed 3L of 1% imazapyr.
2010-07-06 | none found.
CG11 | Plot A, along Old Field Trail
2007-07-27 | sprayed Glypro on 6 small patches
2007-09-07 | sprayed Glypro on 20 small patches
2007-11-02 | sprayed Glypro on 11 small patches
2008-06-19 | no regrowth found
summer | most sprayed twice but some saved until fall (tjw)
2008-11-10 | no regrowth found
2008-12-02 | 8 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2008-12-16 | sprayed Glyphosate on 13 plants
2009-06-01 | none found
2009-09-21 | none found
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-02 | none found.
2010-07-06 | none found.
CG12 | Plot C, S of Old Field Trail, near grid point F4
2007-06-08 | sprayed Glypro on 50 small patches
2007-07-27 | sprayed Glypro on 17 small patches
2007-09-07 | sprayed Glypro on 10 small patches
2007-11-02 | sprayed Glypro on 25 small patches
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-02 | 3 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2009-06-01 | none found, no flags found either
2009-06-29 | none found
2009-09-17 | none found
2009-10-20 | none found.
2009-12-02 | sprayed 2 plants with 1% imazapyr, @ W-end.
2010-06-02 | none found.
2010-07-06 | none found.
*CG13 | SE corner of nPAP N along fire lane to about half way to grid line 4 (Exp. Plot)
2007-06-19 | Exp. started: sprayed Glypro on > 50 small patches on S plot / No treatment on N plot
2007-07-27 | sprayed Glypro on 15 small patches on S plot / No treatment on N plot
2007-09-07 | sprayed Glypro on 3 small patches on S plot / No treatment on N plot
2007-11-02 | sprayed Glypro on 10 small patches on S plot / Extensive growth > 60 on N plot
2008-05-22 | Patches found N & E
2008-06-19 | sprayed Glyphosate on 20S/40N patches
2008-11-10 | S-flagged orange(w/ red tape),Garlon on roots 5 / N-flagged blue,Glyphosate on 67 plants
2008-12-16 | N-sprayed Glyphosate on 38new plants/S-sprayed Glyphosate on 23new plants(outside flagged areas)
2009-06-01 | N-found/ S-found/verified TJW
2009-06-26 | N-16 pink(flagging)= 1% Habitat+.25% Surfactant/ S-16 blue= .25% Habitat+.25% Surfactant
2009-06-29 | sprayed flagged areas
2009-08-25 | All were found dead, no cogan found, only blue flags found.
2009-09-21 | sprayed 57 plants with 1% imazapyr @ S /sprayed 4 plants @ N-half of CG13
2009-10-20 | sprayed 32 withered/15 viable plants with 1% imazapyr.
2009-12-02 | sprayed 50 plants with 1% imazapyr, in N-half mostly new sprouts/18 withered in S-half.
2010-06-02 | sprayed 3L of 1% imazapyr.
2010-07-06 | none found.
2010-09-20 | rg&tw found and treated 4 patches nr resin-flow tree on UPNT: w of trail 7+1 plants, e of trail 7+10
**CG14 | along S side of Main Trail about at grid line F
2007-06-08 | sprayed Glypro on 5 small patches
2007-07-27 | sprayed Glypro on 5 small patches
2007-09-07 | sprayed Glypro on 7 small patches
2007-11-02 | sprayed Glypro on 3 small patches
2008-05-22 | no regrowth found
2008-12-02 | 4 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2008-12-16 | sprayed Glyphosate on 6 new plants
2009-06-01 | found
2009-06-22 | sprayed Glyphosate on 5 plants
2009-07-29 | sprayed Glyphosate on 7 plants
2009-09-17 | sprayed 4 plants with 1% imazapyr.
2009-10-20 | none found.
2009-12-02 | sprayed 7 plants with 1% imazapyr, most new sprouts/2 withered.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
CG15 | just N of Main Trail around big longleaf pine in Plot C
2007-09-07 | sprayed Glypro on 19 small patches
2007-11-02 | sprayed Glypro on 25 small patches
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-02 | none found (tjw)
2008-12-16 | sprayed Glyphosate on 19 new plants found E of tree
2009-06-01 | none found
2009-07-22 | none found
2009-07-29 | sprayed Glyphosate on 9 plants
2009-09-17 | sprayed 4 plants with 1% imazapyr.
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
CG16 | on S side of Main Trail just W of grid line G (which divides Plots C and D)
2007-06-08 | sprayed Glypro on 6 small patches
2007-07-27 | sprayed Glypro on 5 small patches
2007-09-07 | sprayed Glypro on 18 small patches
2007-11-02 | sprayed Glypro on 9 small patches
2008-05-22 | Patches found
2008-06-19 | no regrowth found
2008-11-10 | sprayed 6 plants w/ glyphosate
2008-12-02 | 7 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2008-12-15 | 6 new plants root-treated with Garlon
2009-06-01 | found in abundance/verified TJW
2009-06-22 | sprayed Glyphosate on 31 plants
2009-09-17 | none found
2009-10-20 | sprayed 3 viable plants with 1% imazapyr.
2009-12-02 | sprayed 3 plants with 1% imazapyr, new sprouts.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
*CG17 | just N of Surge Area mini-warehouses and SE of CG1 (Exp. Plot)
2007-06-15 | Exp. started:sprayed Glypro on > 50 small patches on E plot / No treatment on W plot
2007-07-27 | sprayed Glypro on 12 small patches on E plot / No treatment on W plot
2007-09-07 | sprayed Glypro on 19 small patches on E plot / No treatment on W plot
2007-11-02 | sprayed Glypro on 14 small patches on E plot / Lots of growth, not extensive > 50 on W plot
2008-05-06 | no growth E/ patches found in W
2008-06-19 | sprayed Glyphosate on 7W/8E patches
2008-11-10 | E-flagged orange,Garlon on roots 4 patches,13 total / W-flagged blue,Glyphosate on 5 patches, 13 total
2008-12-16 | sprayed Glyphosate on 3 new plants (outside flagged areas)
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes/verified TJW
2009-06-26 | 9pink=1%Habitat+.25%Surfactant/9blue=.25%Habitat+.25%Surfactant/9red=2%Habitat.25%Surfactant
extended experiment into CG1
2009-06-29 | sprayed flagged areas
2009-07-29 | All concentrations are about 1/2 dead (all flagged areas)
2009-08-06 | Blue flags are still alive (barely). Pink are very yellowed and some dead in sun. Red are mostly dead.
2009-08-25 | All were found dead, except questionable:2 red, and 3 blue.
2009-09-17 | sprayed 4 plants with 1% imazapyr, some to the N of sink/retention.
2009-10-20 | sprayed 1 withered/5 viable plants with 1% imazapyr.
2009-12-02 | sprayed 11 plants with 1% imazapyr, ~1/2 withered.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
CG18 | 34th Street berm (added to spray areas July 2006)
2007-06-19 | sprayed Glypro on > 50 of small patches across the whole berm (but less than last year)
2007-07-27 | sprayed Glypro on 8 small patches across the whole berm
2007-09-07 | sprayed Glypro on 9 small patches across the whole berm
2007-11-02 | sprayed Glypro on 8 small patches across the whole berm
2008-05-22 | Patches found from Center ---->N across berm
2008-06-19 | sprayed Glyphosate on 1 on far W patch
2008-11-12 | sprayed Glyphosate on 2 plants 10' E of C8, 3 between B8 & C8, 70 along Berm
2008-12-16 | sprayed 2.5 gal. Glyphosate N to S, E & W of Berm,+ across Firelane@S, across DPI fence@N
2009-06-01 | none found (might have been Johnson Grass before)
2009-07-22 | none found
2009-09-17 | sprayed 86 plants along Berm with 1% imazapyr (in with much Guinnea/Johnson Grass)
2009-09-21 | sprayed 74 plants with imazapyr @ South on W side of Trail/14 plants @ South on E side of Trail
2009-10-20 | sprayed 17 withered plants@S on W side of Trail/14 withered plants @S on E side of Trail.(imazapyr)/
sprayed 20 viable plants W side of Berm, N of GasLine Tr./ 0 on S-half of Berm, & 7 withered on N-half.
2009-12-02 | S-end =8 on E withered, 18 on W withered(of Trail)/53 @ W-side just N of GasL. Tr./10 along N Berm/
50 @ N-end on W side of Berm (coming from other side of fence near 34th St.) .
2010-06-01 | found many @S (new plants?), sprayed 9L imazapyr alond S end. Working towards N, will continue->
2010-06-02 | sprayed 3L of 1%imazapyr @N of Berm(crossover from other side of fence).If cont on DPI-need contact
sprayed 1 plant@ S of Berm on E of Trail. None found on W side of Trail.
2010-07-06 | none found.
2010-08-05 | none found. (heavy cover of Johnson grass now)
**CG19 | Along east border of NATL-w from new corral fence to mini warehouse entrance
2007-06-08 | sprayed Glypro on 6 small patches
2007-07-27 | sprayed Glypro on 5 small patches
2007-09-07 | sprayed Glypro on 6 small patches
2007-11-02 | sprayed Glypro on 5 small patches
2008-05-22 | no regrowth found
2008-12-02 | 1 patch root-treated with Garlon 4 in oil and marked with blue flag (tjw)
2009-06-01 | none found
2009-09-17 | none found
2009-10-20 | none found.
2009-12-02 | sprayed 3 plants with 1% imazapyr @ N of fence/ 1 @ S-end.
2010-06-02 | sprayed 5 plants with 1% imazapyr.
2010-07-06 | none found.
CG21 | just E of CG12 (found June 2006)
2007-06-08 | sprayed Glypro on 20 small patches
2007-07-27 | sprayed Glypro on 22 small patches (New spread to NE of plot)
2007-09-07 | sprayed Glypro on 6 small patches
2007-11-02 | sprayed Glypro on 5 small patches
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-02 | 3 patches root-treated with Garlon 4 in oil and marked with blue flags (tjw)
2009-06-01 | none found
2009-06-29 | none found (pulled flags up)
2009-09-17 | none found
2009-10-20 | none found.
2009-12-02 | sprayed 20 plants with 1% imazapyr, @ S-end.
2010-06-02 | none found.
2010-07-06 | none found.
**CG23 | end of Upland Pine Nature Trail/W side of Hammock Trail @ head (found June 2006)
2007-06-08 | no regrowth
2007-07-27 | no regrowth
2007-09-07 | sprayed Glypro on 10 small patches
2007-11-02 | sprayed Glypro on 3 small patches
2008-05-22 | no regrowth found
2008-07-14 | sprayed Glyphosate on 30 patches
2008-11-12 | sprayed Glyphosate on 5 patches
2008-12-15 | root-treated with Garlon on 6 plants
2009-06-01 | found
2009-06-22 | sprayed Glyphosate on 5 plants
2009-09-17 | sprayed 23 plants with 1% imazapyr.
2009-10-20 | sprayed 4 withered plants with 1% imazapyr.
2009-12-02 | none found.
2010-06-02 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
CG25 | perimeter of mini-warehouse area (added to spray areas July 2006)
2007-06-08 | sprayed Glypro on 10 small patches
2007-07-27 | sprayed Glypro on 25 small patches
2007-09-07 | sprayed Glypro on 18 small patches
2007-11-02 | no regrowth
2008-06-19 | no regrowth found
2008-11-10 | sprayed 10 plants w/ glyphosate
2008-12-16 | root-treated with Garlon on 34 plants, flagged w/ red tape
2008-12-22 | sprayed 12 plants w/ glyphosate @ NE / 27 @SE(mowed)
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes/sprayed 10 plants with Glyphosate
2009-06-22 | sprayed Glyphosate on 5 plants
2009-07-29 | sprayed Glyphosate on 5 plants
2009-09-17 | sprayed 1 plants with 1% imazapyr.
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
**CG26 | SE of Plot E (added to spray areas Nov 2006)
2007-06-08 | no regrowth
2007-07-27 | sprayed Glypro on 2 small patches
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-15 | sprayed Glyphosate (3.5 gal.) on MANY large patches
2009-06-01 | Found, pulled sample up to inspect, has long rhizomes
2009-06-22 | sprayed Glyphosate on 86 plants
2009-09-21 | sprayed 7 plants with 1% imazapyr.
2009-10-21 | none found.
2009-12-02 | sprayed 12 plants with 1% imazapyr, ~1/2 withered.
2010-06-01 | none found.
2010-07-06 | none found.
CG27 | W side of Surge Area Dr., culvert opening & into woods (added to spray areas Aug 2006)
2007-06-08 | sprayed Glypro on 40 small patches
2007-07-27 | sprayed Glypro on 32 small patches
2007-09-07 | sprayed Glypro on 35 small patches
2007-11-02 | sprayed Glypro on 10 small patches
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-22 | sprayed Glyphosate on 3 plants just N of culvert/ 67 NE (fence corner)
2009-06-01 | Found?,pulled sample up to inspect,roots too deep,seems to have rhizomes/sprayed 10 w/ Glyphosate
2009-09-17 | sprayed 13 plants with 1% imazapyr (N fence corner, near Mini Warehouse).
2009-10-21 | sprayed 2 viable plants with 1% imazapyr.
2009-12-02 | sprayed 10 plants with 1% imazapyr, some along endge of woods @ S-end.
2010-06-01 | none found.
2010-07-06 | none found.
**CG29 | E side of Surge Area Dr., culvert opening & into woods (added to spray areas Aug 2006)
2007-06-08 | sprayed Glypro on 9 small patches
2007-07-27 | sprayed Glypro on 7 small patches
2007-09-07 | sprayed Glypro on 6 small patches
2007-11-02 | sprayed Glypro on 6 small patches
2008-05-22 | no regrowth found
2008-12-22 | sprayed 2.5gal (50 +/-) Glyphosate on MANY plants
2009-06-01 | none found
2009-09-17 | sprayed 1 plants with 1% imazapyr.
2009-10-21 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
**CG30 | E side of Surge Area Dr.(added to spray areas Aug 2006)
2007-06-08 | no regrowth
2007-07-27 | sprayed Glypro on 6 small patches (inside fenced parking area…lot of growth)
2007-09-07 | sprayed Glypro on 2 small patches (inside fenced parking area sprayed 10 patches)
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-22 | sprayed Glyphosate on 13 plants
2009-06-01 | none found
2009-07-29 | sprayed Glyphosate on 1 plant
2009-09-21 | sprayed 3 plants with 1% imazapyr.
2009-10-21 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
**CG32 | SE of Plot C (added to spray areas Nov 2006)
2007-06-08 | sprayed Glypro on 18 small patches (N of trail)
2007-07-27 | sprayed Glypro on 20 small patches (N of trail)
2007-09-07 | sprayed Glypro on 25 small patches (N & S)
2007-11-02 | sprayed Glypro on 18 small patches N & S)
2008-05-22 | no regrowth found
2008-06-19 | no regrowth found
2008-11-10 | no regrowth found
2008-12-16 | no regrowth found
2009-06-22 | sprayed Glyphosate on 86 plants north of pole-marker
2009-09-17 | none found
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
^CG33 | SE of Plot A (added to spray areas Nov 2006)
2007-06-15 | sprayed Glypro on >50 small patches
2007-07-27 | sprayed Glypro on 32 small patches
2007-09-07 | sprayed Glypro on 9 small patches
2007-11-02 | sprayed Glypro on 27 small patches
2008-05-22 | Patches found
2008-06-19 | sprayed Glyphosate on 3 patches
2008-11-10 | sprayed Glyphosate on 23 patches
2008-12-16 | sprayed Glyphosate on 23 plants
2009-06-01 | none found
2009-06-26 | sprayed Glyphosate on 4 plants
2009-06-29 | sprayed 4 more plants (possibly same plants)
2009-09-21 | sprayed 10 plants with 1% imazapyr.
2009-10-20 | none found.
2009-12-02 | sprayed 25 plants with 1% imazapyr, @ W-end.
2010-06-02 | none found.
2010-07-06 | none found.
** *CG35 | W on S Trail, close to 34th St. Trail: both sides of trail (added Nov 2006) (Exp. Plot)
? | was sprayed in past (could see thatch)
2007-06-15 | Exp.t stared on S of trail: sprayed Glypro on 3 small patches on W plot / no treatment E plot
2007-06-15 | sprayed Glypro on 12 small patches on N side of trail (not included in experiment)
2007-07-27 | sprayed Glypro on 5 small patches on N side of trail /exp: 2 sprayed on west side
2007-09-07 | sprayed Glypro on 3 small patches on N side of trail /exp: 0 sprayed on west side (no regrowth)
2007-11-02 | Plot damaged by fence contractor installing new property line fence (did not treat)
2008-05-22 | no regrowth found
2008-12-22 | no regrowth found
2009-10-20 | none found.
2010-06-01 | sprayed 16L of imazapyr 1% mix on all plants found
2010-07-06 | found some with yellowed/wilted blades, left to observe if they will die on own (check next month).
2010-08-05 | none found. (Johnson grass cover)
^CG37 | Center Plot A, including grid pt. F3 along Trail (added May 2008/formerly part of CG7).
2008-05-06 | sprayed Glyphosate on 15 small/medium patches
2008-06-19 | sprayed Glyphosate on 3 patches
2008-11-10 | sprayed 70 plants w/ glyphosate
2008-12-16 | sprayed Glyphosate on 10 plants
2009-06-01 | none found, pulled 2 samples up to inspect, no evidence of rhizomes
2009-06-29 | sprayed Glyphosate on 11 plants
2009-09-17 | sprayed 10 plants with 1% imazapyr.
2009-10-20 | sprayed 3 withered/2 viable plants with 1% imazapyr.
2009-12-02 | sprayed 7 plants with 1% imazapyr, (3 were new sprouts).
2010-06-02 | sprayed 3 plants with 1% imazapyr.
2010-07-06 | none found.
^CG38 | across firelane from CG9, in nPAP (added Dec 2008)
2008-12-15 | found
2008-12-16 | sprayed Glyphosate on 10'x10' patch (30+/-)
2009-06-01 | none found
2009-09-21 | none found
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-02 | none found.
2010-07-06 | none found.
CG39 | NE of PLOT B, N of Trail (added Dec. 2008)
2008-12-16 | sprayed Glyphosate on 40+/- plants in large patch
2009-06-01 | none found, pulled sample up to inspect, has no rhizomes & deep purple base
2009-09-21 | none found, had been sprayed for Johnson Grass previously.
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
CG40 | along Firebreak from C11-C12
2009-02-25 | found in abundance (*might be Johnson Grass, as CG2 was)
2009-09-21 | sprayed 356 plants with 1% imazapyr.
2009-10-20 | sprayed 111 plants with 1% imazapyr, mostly withered (in shady area), Guinnea Grass is in area.
2009-12-02 | sprayed 52 plants with 1% imazapyr, withered.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found. (thick Guinnea grass cover now)
CG41 | along W side UP Trail, NW of CG13
2009-06-29 | sprayed 1.5 gal. Glyphosate on +/-50 plants in 2 large patches
2009-09-17 | pulled up 7 plants by hand w/ rhizomes.
2009-10-20 | none found.
2009-12-02 | none found.
2010-06-01 | pulled up 10 plants w/rhizomes by hand.
2010-07-06 | pulled up 1 plant w/rhizomes by hand.
*CG | Experimental Plot
**CG | no regrowth found by RG before rains (drought 22-May-08).
^CG | no regrowth found by RG before rains (drought 4-May-09).
~(CG42)? | East side of NATL-e @fence, on Med Bldg side(N of Boardwalk)
2010-06-01 | found large patches on E side of fence (not too likely to cross over fence).

## cogon "no regrowth"
NATL invasives: cogongrass
no regrowth found in 2008
TJW in charge through 26 Jul 06; Kevin Ratkus in charge from then until 2 Nov 07.
Robert Guggenheim put in charge 6 May 08.
CG3 | at NE corner of Plot A
2007-06-15 | sprayed Glypro on 5 small patches
2007-07-27 | no regrowth
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-06 | no regrowth found
2008-12-16 | no regrowth found
2009-10-20 | none found.
**CG5 | at S end of mulched trail from Powell Hall
2007-06-15 | sprayed Glypro on > 50 small patches along fence & 20 small patches next to bench
2007-07-27 | sprayed Glypro on 2 small patches
2007-09-07 | sprayed Glypro on 3 small patches
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-16 | no regrowth found
2009-10-20 | none found.
CG9 | Plot A, near gridline F and Old-field Trail (3 connected patches)
2007-06-08 | No regrowth found
2007-07-27 | No regrowth found
2007-09-07 | No regrowth found
2007-11-02 | No regrowth found
2008-05-22 | no regrowth found
2008-12-16 | no regrowth found
2009-10-20 | none found.
**CG20 | just east of NV 1 (n of Main Trail nr. Pavilion) (found June 2006)
2007-06-08 | no regrowth
2007-07-27 | no regrowth
2007-09-07 | sprayed Glypro on 7 small patches
2007-11-02 | sprayed Glypro on 2 small patches
2008-05-22 | no regrowth found
2008-12-02 | too overgrown with weeds to check (tjw)
2008-12-22 | no regrowth found
2009-10-20 | none found.
CG22 | along fence behind Haz Mat building (E side of East Trail) (found June 2006)
2007-06-15 | sprayed Glypro on 3 small patches
2007-07-27 | no regrowth
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-16 | no regrowth found
2009-10-20 | none found.
**CG24 | just W of CG 15, with Baccharus understory (found June 2006)
2007-06-08 | sprayed Glypro on 12 small patches (north of trail)
2007-07-27 | sprayed Glypro on 5 small patches
2007-09-07 | sprayed Glypro on 4 small patches
2007-11-02 | sprayed Glypro on 5 small patches
2008-05-22 | no regrowth found
2008-12-16 | no regrowth found
2009-10-20 | none found.
CG28 | E side of Surge Area Dr. (added to spray areas Aug 2006)
2007-06-08 | sprayed Glypro on 8 small patches
2007-07-27 | no regrowth
2007-09-07 | no regrowth
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-22 | no regrowth found
2009-10-20 | none found.
CG31 | S-central of Plot D (added to spray areas Nov 2006)
2007-06-08 | no regrowth
2007-07-27 | no regrowth
2007-09-07 | no regrowth (plot disked)
2007-11-02 | no regrowth (plot disked)
2008-05-22 | no regrowth found
2008-12-22 | no regrowth found
2009-10-20 | none found.
**CG34 | N-central of Plot D (added to spray areas Nov 2006)
2007-06-08 | sprayed Glypro on 20 small patches (north of trail)
2007-07-27 | sprayed Glypro on 3 small patches (north of trail)
2007-09-07 | no regrowth (plot disked)
2007-11-02 | no regrowth (plot disked)
2008-05-22 | no regrowth found
2008-12-16 | no regrowth (plot disked)
2009-10-20 | none found.
**CG36 | Entrance of NATL-E (added to spray areas June 2007)
2007-06-08 | sprayed Glypro on 8 small patches (N of entrance trail)
2007-07-27 | no regrowth
2007-09-07 | sprayed Glypro on 3 small patches
2007-11-02 | no regrowth
2008-05-22 | no regrowth found
2008-12-22 | no regrowth found
2009-10-20 | none found.
*CG | Experimental Plot
**CG | no regrowth found by RG before rains (drought).

## skunkvine
NATL invasives: skunk vine
TJW turned over treatment of skunkvine to Robert Guggenheim in spring 2008.
RG turned over to Lary Reeves in late summer of 2010.
Gasline N= | between gridpoints E10 and F10 on north side of Gasline Trail
2007-06-29 | sprayed 1 gal glyphosate on 30 minor vines and 7 medium ones
2007-07-17 | sprayed ca 2 qt glyphosate on 5 minor vines, 2 medium ones, and 3 major ones (two of these >15' in tree tops)
2007-08-04 | sprayed glyphosate on 6 minor vines, 2 medium ones, and 3 major ones (previously missed)
2007-08-15 | sprayed glyphosate on 5 minor vines, and 6 medium ones. Used Garlon 4 in oil on stems of major vines
2007-08-31 | sprayed glyphosate on 9 minor vines, 3 medium ones, and 2 (previously missed) major ones
2007-11-28 | sprayed Garlon 4 in oil on 12 minor vines and 10 medium ones (no major ones found)
2008-06-19 | sprayed glyphosate on 12 patches, flagged each w/ orange tape
2008-07-22 | sprayed glyphosate on 20+/- patches,pulled 5 out of trees
2008-08-15 | sprayed 3.5gal Glyphosate(+/-60 total),cut & put Garlon on40+/-of those in trees,found 1 in tree w/flowers(Garlon'd it!)
2008-08-27 | sprayed 3.5 gal. 3% mix Glyphosate (usually only 2%), marked with pink flags and ribbon, 60+/-
--cut and put Garlon on 3 more vines in trees, marked with orange ribbon--
2008-09-10 | sprayed 4 more on ground with glyphosate
2008-10-06 | sprayed 3 more (one group was quite large towards trail on east)
2008-11-12 | sprayed 1 w/ glyphosate in NE area, marked w/ red flag
2009-05-06 | All Flags have been removed (Vandalism)…
sprayed a larger patch in W+ cut 2 out of tree= total 5 plants/+ sprayed 4 isolated plants/…
+sprayed larger patch in NE, 5 plants/ (glyphosate on all and marked w/red flags)
2009-06-01 | none found
2009-07-22 | none found
2009-09-10 | sprayed 15 plants with glyphosate. (seems to be most active in Aug and Sept!)
2009-10-12 | none found !
2009-11-02 | none found
2009-12-16 | no regrowth found.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | 2 found and treated
Gasline S= | between gridpoints E10 and F10 on south side of Gasline Trail
2007-06-29 | sprayed 0.5 gal glyphosate on 12 minor vines and 3 medium ones
2007-07-17 | sprayed ca 1 qt glyphosate on 8 minor vines, 4 medium ones, and 2 major ones
2007-08-04 | sprayed glyphosate on 5 minor vines, 1 medium, and 2 major ones (ran out of spray; did not complete search)
2007-08-15 | sprayed glyphosate on 4 minor vines and 1 medium one. Used Garlon 4 in oil on stems of 2 major vines.
2007-09-05 | sprayed glyphosate on 9 minor vines and 6 medium ones.
2007-11-29 | sprayed glyphosate on 6 minor vines and 5 medium ones. Used Garlon 4 in oil on stems of 3 major vines.
2008-06-19 | sprayed glyphosate on 2 patches, flagged each w/ orange tape
2008-07-22 | sprayed glyphosate on 50+/- patches,pulled 15 out of trees
2008-08-15 | cut and put Garlon on 20 +/- vines in trees
2008-08-27 | sprayed 3% mix Glyphosate (usually only 2%), marked with orange ribbon, 8 patches
--cut and put Garlon on 4 more vines in trees, marked with orange ribbon--
2008-09-10 | sprayed 3 more on ground with glyphosate
2008-10-06 | none found
2008-11-12 | none found
2009-05-06 | none found
2009-06-01 | none found
2009-07-22 | none found
2009-09-10 | cut and sprayed garlon on vines in trees, Sprayed 42 total plants with glyphosate. (most active in Aug and Sept!)
2009-10-12 | found only 2 plants @ SE section, sprayed w/glyphosate.
2009-11-02 | none found
2009-12-16 | no regrowth found.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
Gasline S2= | between gridpoints G10 and H10 on south side of Gasline Tr. (Area is 25mX40m= ~1,000 square meters)
2009-08-25 | cut open area for sprayer truck to come and access for spraying, marked area with orange flagging.
was sprayed a few days after.
2009-09-08 | opened up more for truck to come back and spray again.
was sprayed a few days later
(seems to be most active in Aug and Sept!)
2009-09-17 | Cleared area down to eye-level for easier treatment, cut and Garlon some larger vines first.
2009-10-12 | 1vine missed,otherwise very small number of new growth towardws N-half/sprayed 37 new,& 1old patch w/glyphosate.
2009-11-02 | none found
2009-12-16 | pulled up 2 vines by hand @ NW area on base of fallen tree.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.

## ardisia
NATL invasives: coral ardisia
2008 data taken from NATL log for 2008; jr=Julian Resasco (Graduate TA), Work continued by Robert Guggenheim in 2010
RG turned over to Lary Reeves in late summer of 2010. TJW took charge of Ardisia project and reported events in http://natl.ifas.ufl.edu/ArdisiaPlan.pdf
date | source | event
2007 |  | no action taken
2008-02-09 | jr | jr and volunteers from Alpha Phi Omega remove Ardisia from 1 ha in SE hammock area (corners F10,H10,H12,F12)
2008-02-20 | jr | jr removes all Ardisia visible from hammock trail and main trail
2008-03-01 | jr | jr removes all Ardisia visible from Hammock Trail
2008-03-01 | jr | jr and volunteer Ben Saver remove Ardisia from corners H8, I8, I12, H12 and F8, H8, F10, H10
spring 2008 | jr | volunteer Ben Saver removes Ardisia from corners E11, F11, F12, E12 and southern half of corners D11, E11, E12, D12
2008-03-31 | tjw | volunteer Robert Gugenheim works 8 hours removing Ardisia from both sides of East Trail between Main and Division Trails
2008-03-31 | tjw | volunteer Robert Gugenheim could find no more Ardisia on the east side of East Trail between Main and Division Trails
2008-03-31 | tjw | Marissa Strifel removes all Ardisia that she can find in NATL-east
2008-06-04 | tjw | volunteer Ben Saver, with help from Marissa Streifel, removes all Ardisia from the west side of the east sRAP fire lane.
2008-06-12 | tjw | volunteer Ben Saver completes removal of Ardisia from block D11, D10, E10 (completing all blocks south of Gasline Trail)
2008-08-28 | tjw | volunteer Ben Saver completes removal of Ardisia from block D9, D8, E9, E8 (completing all blocks south of Division Trail)
2009-11-02 | rg | removed many plants on sRAP Firebreak @ S end, and many around G12.
2009-07-01 | rg | Geraldo Celis & Corrie Pieterson (volunteers) located and removed all plants found throughout NATL-w from E5 south & east
2010-01-27 | rg | found and notated density and location of remaining plants from previous year, most dense in D11, E11, & D12-H12
2010-02-02 | rg | Removed plants and berries throughout NATL-e/w and put pink flags to notate location, & notated on map. 96 in E./212 in W
2010-04-15 | rg | Began spraying new and remaining plants throughout NATL using 3.5 gal water to 9oz Garlon 4 to 2tbsp Dyne-Amic for mix.
Completed sprayNATL-e[K5=14,L5=66,K6=10,L6=7,L10=1]&started in NATL-w.Replaced any short flags w/Tall Pink Flags.
2010-05-01 | rg | Completed spraying most of NATL-w Restricted Area. ~17 gal Garlon/Dyne-Amic/water mixure used so far.
2010-05-03 | rg | Completed spraying in NATL-w Restricted Area, and started moving north into the Public Area. Used ~7 gal of mix.
2010-05-05 | rg | Complt'd all of NATL-w Public area.Made a map of locations.See"NATL-w Public Ardesia Map(2010).jpg".Used 4 gal of mix.
2010-07-21 | rg | check all locations with flags and count, spray, and flag any new plants or regrowth (~220 new small plants).
2010-07-22 | rg | sprayed ~50 plants and marked on map locations of plant patches.
2010-07-26 | rg | sprayed in Public Area for 3 hours.

## Johnson&Guineagrass
NATL invasives: Johnson grass and Guinea grass
Bob Guggenheim in charge, starting July 2008
RG turned over to Lary Reeves in late summer of 2010.
OF Plot A
2008-07-08 | Sprayed glyphosate on many large patches. Est. 40+/-.(mostly Guinea)
2008-11-12 | Sprayed glyphosate on 10 small patches(Guinea)
2009-06-26 | Sprayed 0.5 gal glyphosate on south edge (Guinea)
2009-06-29 | Sprayed 1 large patch on N edge/15+/- plants in S center/70 in SE (all glyphosate)
2009-07-30 | Sprayed 6.5 gal glyphosate
2010-07-12 | Sprayed 1 Gal throughout.
OF Plot B
2008-07-08 | TJW sprayed glyphosate on most clumps along East Trail
2008-07-23 | Spray 3.5gal. glyphosate on many large patches. Est. 50+/-.
2009-06-09 | Sprayed 1 gal. of glyphosate on se section, new sprouts after bush hog, needs more spraying. (Johnson)
2009-06-15 | Sprayed 3.5 gal. of glyphosate on se section, new sprouts after bush hog.
2009-06-22 | Sprayed 3 gal. of glyphosate on se section, new sprouts after bush hog, finished spraying.
2009-06-26 | Sprayed 1.5 gal glyphosate on missed plants (Johnson)
2009-07-22 | Sprayed 3.5 gal glyphosate (x5)
2009-07-29 | Sprayed 5.0 gal glyphosate
2009-07-30 | Sprayed 3.5 gal glyphosate
2010-07-07 | sprayed Glyphosate on plants to prevent seeds.
2010-07-12 | Sprayed 1 Gal throughout.
2010-07-26 | sprayed remaining plants in area
OF Plot C
2008-07-14 | Sprayed glyphosate on many large patches. Est. 110+/-.(mostly Guinea)
2009-06-29 | Sprayed along firebreak on W edge/ 2 gal (+/-150 plants) in center, needs much more on W (all glyphosate)
2009-07-05 | Sprayed 4 gal. glyphosate on many patches in W and to the south along OF Trail
2009-07-13 | Sprayed 3 gal. glyphosate along W edge
2009-07-29 | Sprayed glyphosate on 30 plants
2010-06-24 | Sprayed 40 plants with glyphosate along Firebreak & N-end OF NT to prevent seeding.
2010-07-12 | Sprayed 1 Gal throughout.
OF Plot D
2008-07-14 | Sprayed glyphosate on many large patches. Est. 45+/-.(mostly Johnson)
2008-11-10 | Sprayed 10 +/- small patches w/ glyphosate
2009-06-26 | Sprayed 0.5 gal glyphosate on nw corner (Guinea)
2009-06-29 | Sprayed glyphosate on one spot along Main Trail (Johnson)
2009-07-05 | Sprayed glyphosate on 10 plants in W
2009-07-29 | Sprayed 3 gal glyphosate
2010-07-12 | Sprayed 1 Gal throughout.
OF Plot E
2009-06-01 | Sprayed 3 gal. glyphosate on many patches (Johnson)
2009-07-29 | Sprayed glyphosate on 110 plants
2009-08-27 | Sprayed 3.5 gal glyphosate near pavilion.
2009-10-26 | Sprayed from Pavilion to 50' W, ~15 plants w/ glyphosate. Cleared this area for public usage.
2010-07-07 | sprayed Glyphosate on plants to prevent seeds.
2010-07-12 | hand pulled around 30+ plants durring rain.
nPAP | on SE corner and along E side of UP Trail headed N
2008-07-14 | Sprayed glyphosate on many small patches. Est. 25+/-.(mostly Johnson)
2009-07-05 | Sprayed 3.5 gal glyphosate on many new patches after burn (mostly Johnson)
2009-07-13 | Sprayed 3.5 gal. glyphosate along firebreak to the E and along UP Trail @ Main Trail
2009-08-03 | Pulled"Johnson"by Hand for 6 hrs,Started Exp.3 Plots=3x3 meters each@SE. N-pulled,M-natural,S-sprayed Glyphosate
Rained @ 3pm
STARTING NEW ENTRY see: PAP
2010-06-01 | regrowth seen in middle of area E of UP Trail/suggest spraying while sprouting.
2010-06-24 | sprayed 3.5 gal of Glyphosate on tallest plants to prevent seeds.
2010-06-28 | sprayed 3.5 gal of Glyphosate on tallest plants to prevent seeds.
2010-07-06 | sprayed small patch N of GridLine 4.
2010-07-07 | sprayed all plant patches left after hand-pulling
SEEP | Sprayed 7gal. glyphosate on many large patches. Est. 135+/-.
2008-07-15 | Sprayed 1.5gal. glyphosate W of Pavilion. Est. 20+/-
2008-07-23 | Sprayed 0.5 gal. Glyphosate along e of Trail @ se corner of Plot B (Johnson)
2009-06-09 | Sprayed 0.5 gal. Glyphosate along e of Trail @ se corner of Plot B (Johnson)
2009-06-22 | Sprayed glyphosate on 10 plants along e of Trail @ se corner of Plot B (Johnson)
2009-07-29
2010-07-07 | sprayed Glyphosate on plants to prevent seeds.
2010-07-12 | Sprayed 1 Gal throughout E along Plot B.
sPAP | Sprayed 0.5 gal. glyphosate on Johnson in SE corner (Johnson)
2008-10-14 | Sprayed 0.5 gal. glyphosate along E (Johnson)
2009-07-05 | Sprayed 0.5 gal. glyphosate on a few plants in N & along N UP Trail & a few plants along firebreak to E,
2009-07-13 | Sprayed 3 gal. glyphosate until attacked by bees in SE, sprayed rest along Division Tr. Headed E until sprayer broke.
STARTING NEW ENTRY see: PAP
cut tops of all germinating plants.
2009-09-08 | sprayed 7 gal glyphosate in S-half, from UP Trail all the way to Division Trail (around exp. Plots).
2009-09-10 | sprayed 0.5gal glyphosate in SW corner on remainder of grass.
2009-09-15 | regrowth seen @ S-half.
2009-11-02 | regrowth seen @ S-half/ needs a lot of attention.
2010-06-01 | sprayed 7 gal of Glyphosate on tallest plants to prevent seeds.
2010-06-24 | sprayed 3.5 gal of Glyphosate on tallest plants to prevent seeds.
2010-06-28
2010-07-07 | sprayed all plant patches left after hand-pulling
2010-07-12 | Sprayed 8x3.5 Gal throughout S-half to prevent seed crop and irradicate the remaining plants.
BERM | along 34th St. Trail
2009-07-22 | Sprayed 3.5 gal glyphosate @ Gasline Trail
2009-08-13 | Many germinating plants along N-half.
nRAP
2010-06-24 | sprayed 20 plants with Glyphosate along Division Trail to prevent seeds.
2010-07-16 | sprayed 2 larger patches
sRAP | along Firebreak from C11-C12 & around A12 Trail area
2010-06-01 | many plants sprouting along Trails and Firebreak/suggest spraying while sprouting.
2010-07-16 | sprayed 20 gal on all live plants.
PAP- | experimental and hand removal
nPAP
2009-08-03 | Pulled"Johnson"by Hand for 6 hrs,Started Exp.3 Plots=3x3 meters each@SE. N-pulled,M-natural,S-sprayed Glyphosate
Rained @ 3pm
2009-08-06 | Pulled by hand for 7.5 hrs, Removed all "Johnson" from W of UP Trail. Removed all from N-half, on E of Trail.
Removed Largest from S-half. Systematically removing "Johnson" from areas by size of plants. Removing Largest first.
Removing Largest plants first to prevent Germination.
Rained for a half hour around 1pm.
2009-08-13 | Spread out previously pulled plants along trails for further drying, plants were rooting.
No regrowth thus far in N exp. Where pulled. S plot is all dead from spray.
2009-09-08 | cut tops of all germinating plants.
2009-09-14 | pulled plants for 1hr.
2009-09-15 | N-very few small new plants/ M-fallen over & germinated/ S-dead with small undergrowth/ pulled 44 W of trail.
2009-09-28 | N-removed 4 plants by hand/M-leaned all plants inward to prevent germ. Others/S-all dead/remove all remaining …
plants in area except near poison oak, ~2hrs.
2010-06-28 | Hand pulled all grass from both N exp. Plots. Bio mass in each section was 1 (least) to 3 (most).
W exp=N-3, M-1, S-2/ E exp= N-1, M-2, S-3. Will use Glyphosate in M & Smith Mix in S.
2010-07-06 | pulled all plants N of GridLine 4. used Glyphosate in M & Smith Mix in S exp.plots
2010-07-07 | pulled all plants that seem to be isolated and not in patches throughout.
2010-07-26 | pulled al remaining plants
sPAP
2009-08-06 | Most plants are in S-half. N edge has small plants that survived spraying. Also in NW a large patch not flowered, yet.
S-half is flowered and may Germinate soon. Planning to set up 2 of the "Exp.3 Plots=3x3 meters each" @ S edge.
2009-08-13 | Pulled up plants@N edge,&along W. Started 2 Exp.Plots@S edge.Sprayed 5x 3.5gal Glyphosate on Tall plants@S-half.
Pulled plants in N of Exp. Plots, Middle left alone as control, and S sprayed.
2009-09-08 | cut tops of all germinating plants.
2009-09-15 | N-couple small new plants/ M-tall & germinating/ S-dead with small undergrowth.
2010-06-28 | Hand pulled all grass from N exp. Plot. Bio mass in each section was 1 (least) to 3 (most). exp=N-2, M-3, S-1.
Will use Glyphosate in M & Smith Mix in S.
2010-07-06 | used Glyphosate in M & Smith Mix in S exp.plots
2010-07-07 | pulled all plants that seem to be isolated and not in patches throughout.
2010-07-26 | pulled any remaining plants around Restoration Islands and in N-half

## air potato
NATL invasives: air potato
TJW turned over treatment of air potato to Robert Guggenheim in June 2008.
RG turned over to Lary Reeves in late summer of 2010.
E8= | north of gridpoint E8 in se corner of sPAP and sw corner of PAH; along the south end of the fire lane between the two
2007-06-30 | sprayed glyphosate on 15 vines that were less than 2ft up and on 2 that were 4-6ft up
2007-08-04 | sprayed glyphosate on 22 vines that were less than 2ft up, 6 that were 2-6ft up, and 1 that was >6ft up
2007-09-05 | sprayed glyphosate on 14 vines that were less than 2ft up, 2 that were 2-6ft up, and 1 that was >6ft up
2007-11-29 | sprayed glyphosate on 1 vine that was covering small palm 20ft s of cat claw tree (w edge of firelane); ca 50 potatoes
removed, some nearly as large as golf balls
2008-06-19 | sprayed glyphosate on 3 small patches E of Firelane/ 0 W of Firelane
2008-07-22 | sprayed glyphosate on 10 small patches E of Firelane/ 10 W of Firelane
2008-08-27 | sprayed glyphosate on 16 patches E of Firelane/ 3 W of Firelane
2008-09-10 | sprayed 1gal (+/-10plants) Glyphosate on sPAP patches
2008-10-14 | sprayed 7 on , and 3 on E of firelane with glyphosate
2008-11-12 | none found in E, 1 in W, sprayed with glyphosate
2009-06-09 | sprayed 5 plants with glyphosate in PAH side of firelane/ Flagged orange
2009-07-22 | none found
2009-09-10 | sprayed 2 plants with glyphosate in sPAP.
2009-10-12 | pulled up 6 plants & sprayed glyphosate on1 larger patch@1.5ft.high in PAH/none found in PAP(grass all sprayed/dead)
2009-11-02 | pulled up 2 plants/bulbs near flags in PAH.
2009-12-16 | no regrowth found.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | found plants along NW side, S and far W all along trails with Orange "air potato" flags
CCW= | just north of Classic Carwash on both sides of South Trail
2007-06-30 | sprayed glyphosate on 14 vines that were less than 2ft up, on 5 that were 4-6ft up, and on 3 that were >6ft up
2007-08-04 | sprayed glyphosate on 1 vine that was less than 2ft up and 1 that was 2-6ft up
2007-09-05 | sprayed glyphosate on 4 vines <2ft up, on 2 that were 4-6ft up, and on 1 that was >6ft up (nr. Archer Woods)
2007-11-29 | none found
2008-06-19 | sprayed glyphosate on 28 W of S Trail/ 21 E of S Trail (will re-examine to authenticate they are potato vines)
2008-07-22 | sprayed glyphosate on 15 W of S Trail/ 15 E of S Trail
2008-08-27 | sprayed glyphosate on 10 small patches E of Firelane/ 3 W of Firelane
2008-10-14 | none found
2008-11-12 | none found
2009-06-09 | found many plants, took samples, from South Trail to Unity Trail. Verified as air potato. (mostly between I-J Grid Lines)
2009-06-10 | FLAGGED "BULBIFERA" ORANGE & REMOVED 10 BULBS/FLAGGED "FLORIDANA" BLUE, LEFT ALONE/FLAGGED UNKNOWN PLANTS YELLOW
2009-07-22 | none found
2009-08-25 | pulled up 3 small plants w/bulbs @ orange flags.
2009-09-08 | Pulled up4bulbs by flags near Unity Trail.Sprayed1gal(+/-10plants)glyphosate@CCW/AllState fence(See new AllState).
2009-09-17 | sprayed 60 plants on Archer Woods Apt. side of fence @ W side of CCW.
2009-10-12 | pulled up 3 plants near orange flags (1 @2ft. High w/pea sized bulbs along vine/other plant growing from pea size bulb).
none found along fences.
2009-11-02 | pulled up 2 plants/bulbs @ S end towards AllState, marked with orange flag. None found @ AW Apts.
2009-12-16 | no regrowth found.
2010-06-01 | none found.
2010-07-06 | hand removed 6 small new plants/bulbs on N of S Trail.
2010-08-05 | plant found N of S Trail, ~ Center of CCW prop. @ Southernmost Orange flag.
NATL-e= | east edge of NATL-east and Emmer property between boundary fence and road
2007-06-30 | evaluated but did not spray: found 3 small sprouts [vines were luxuriant on SW corner of Emmer property]
2007-08-04 | sprayed glyphosate on 28 vines that were less than 2ft up and 2 that were 2-6ft up (one of these had 2 small air tubers)
2007-09-05 | sprayed glyphosate on 22 vines that were less than 2ft up
2007-11-29 | one 1-leaf sprout found and sprayed
2008-06-19 | sprayed glyphosate on 39+ large patches
2008-07-23 | sprayed glyphosate on 30+ new small patches (last spray seemed to work)
2008-09-10 | sprayed glyphosate on 22 new small patches
2008-10-14 | sprayed glyphosate on 7 new small patches (Cut growth in 2 trees on medical plaza side to prevent spreading to NATL)
2008-11-12 | sprayed glyphosate on 2 plants- 1 small, 1 yellowed-resiliant from last spray
2009-06-09 | sprayed glyphosate on 12 small plants, some climbing fence, and oversprayed onto other side of fence 1-2 ft.
2009-07-22 | none found
2009-08-27 | Sprayed 1gal. glyphosate on 5small plants& over sprayed(+/-10)in next property.LARGE patches on E side of fence.
2009-09-10 | sprayed 3 small plants with garlon while there for arrowhead.
2009-09-15 | sprayed 1 small plant in fence/ sprayed 10 outside fence to S/ @Gridline 7 cut large plants out of trees outside fence.
2009-10-12 | 2 bulbs pulled @ far N & 1 pulled midway-all inside fence.
2009-10-26 | spray all plants E of fence @ N end on Med. Bldg. side, ~40 w/ glyphosate.
2009-11-02 | none found W of fence.
2009-11-26 | none found.
2010-06-02 | sprayed ~30 new plants@N end on E of fence (Med Bldg side) along fence.
2010-07-06 | hand removed 3 small new plants/bulbs from inside fence on N end.
2010-08-12 | hand removed 1 small on W of fence/many found on E of Fence @ N&S. Needs spray at least @N.
AllState= | East of CCW, near J12, along fence bordering CCW, inside bushes
2009-09-15 | sprayed 3 gal (+/-30 plants) glyphosate and pulled tops out of bushes & trees.
2009-10-12 | none found, only ivy and bushes remained.
2009-11-02 | none found.
2009-12-16 | no regrowth found.
2010-06-01 | none found.
2010-07-06 | some regrowth found, need to watch/get permission to spray.
2010-08-05 | regrowth inside Allstate prop. Near CCW fence
NATL-e2= | E side of fence ~between Grid Lines 9-10. On Med. Bldg. side w/ permission
2009-10-05 | 2.5hrs. Cutting out of trees, starting at south. Iterupted by wasp sting.
2009-10-12 | cont. cutting 1.75hrs. +sprayed 1.5gal. (+/-20plants) glyphosate on southernmost end.
2009-10-13 | sprayed 3.5gal. (+/-40plants)Glyphosate cont. from S towards N.
2009-10-21 | 2gal. (+/-20plants) @ center & W side with glyphosate.
2009-10-26 | sprayed 3.5gal. (+/-40plants) Glyphosate cont. from center towards N.
2009-11-02 | all dead @ S-half. N-half season end- wilting.
2009-11-26 | spoted some growing in middle of marsh, E of boardwalk.
2010-06-01 | some regrowth found @ S-half.
2010-07-06 | none found.
2010-08-12 | E of fence @ S found many
Gasline S= | between gridpoints E10 and F10 on south side of Gasline Trail
2008-07-22 | sprayed glyphosate on 16 patches
2008-11-12 | sprayed glyphosate on what looked like 1
2009-06-09 | none found
2009-07-22 | none found
2009-11-02 | none found
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | none found.
No longer found in site:
sPAP= | between six-pine set no. 44 and 45 in southeast quadrant of sPAP
2007-07-17 | none found, but 1 vine seen and removed previously during weeding of restoration islands
2007-08-04 | none found
2007-09-05 | none found
2007-12-03 | none found
2008-09-01 | none found
2009-09-01 | none found
2010-06-01 | none found.
UP#17= | where UP Nature Trail crosses firelane on east edge of sPAP
2007-07-17 | two low vines sprayed with glyphosate
2007-08-04 | none found
2007-09-05 | none found
2007-12-03 | none found
2008-09-01 | none found
2009-09-01 | none found
2010-06-01 | none found.

## arrowhead
NATL invasives: arrowhead vine (Syngonium podophyllum)
TJW turned over treatment of arrowhead vine to Robert Guggenheim in summer 2008.
RG turned over to Lary Reeves in late summer of 2010.
AV1= | North & south side of South Trail, between G12 & H12 (started from house plants thrown over fence)
2006-11-17 | sprayed Glypro on large patch of vines
2006-11-22 | finished spraying Glypro on large patch of vines
2007-12-03 | sprayed glyphosate on 15 small, 5 medium, and 3 large patches. (Fence work had disrupted most growth south of trail.)
2008-07-07 | TJW found water oak with vigorous vines ascending, infestation extending 25' eastward and 35' westward;all treated(~20)
2008-07-22 | sprayed glyphosate on 15+/- patches, pulled 5 out of tree and sprayed roots left on tree
2008-08-27 | sprayed glyphosate on 100+ patches, up into woods
2008-10-14 | sprayed 1.5gal (+/-15patches) glyphosate on MANY patches
2008-11-12 | none found along trail on N or S, may be dormant after last spray?
2009-06-09 | sprayed glyphosate on 105 plants on N side of S Trail
2009-09-08 | Sprayed 2.5gal (+/-25patches) Glyphosate along N side of trail in E-half. Need to cont to W-half and on S of trail.
2009-09-10 | sprayed 2L Garlon(+/-30patches)on W side of arrowhead,around G12, & all of S side of trail. **(switched to Garlon+oil).
2009-09-21 | Glyphosate plants seem uneffected, while Garlon seems to have worked well. Need to respray NE-half.
2009-09-30 | Glyphosate still green and vibrant/Garlon all dead, no trace. Respray all glyphosate areas(~25) @E-half w/ Garlon.
2009-10-12 | Little effect so far, waiting to see expected mortality to respray.
2009-11-02 | pulled up 6 plants with long rhizomes(roots-stems) on W end @ N of trail/none found E /none found @ S of Trail.
2009-12-16 | no regrowth found.
2010-05-11 | checked, no sign of regrowth so far.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-05 | small sprouts found west to east along N side of Trail, none found on S side of Trail.
AV2= | north end of chain link fence along NATL-east border with medical complex, from around O9 to O7
2007-12-03 | heavy infestation; sprayed outliers with glyphosate [est at 20 patches in for 2009 summary]
2007-12-14 | used 2 gal (+/-20patches) of glyphosate to spray entire infestation
2008-06-19 | sprayed glyphosate on 20+/- patches
2008-07-23 | sprayed glyphosate on 100+/- patches
2008-09-10 | sprayed 1 gal (+/-10patches) glyphosate on many patches, hard to count (in bunches)
2008-11-12 | sprayed glyphosate on 25 patches-many small,new growth or yellowed leaves-resiliant from last spray
2009-06-09 | sprayed glyphosate on 139 plants, mostly N of O7-many small,new growth
2009-07-22 | small new patches found, needs spraying
2009-08-27 | Sprayed 2.5 gal (+/-25patches) glyphosate along fence and over sprayed into next property.LARGE patches E of fence.
2009-09-10 | sprayed 1LGarlon(+/-15patches) along trail inside NATL. glyphosate seems too little effective. **(switched to Garlon+oil).
2009-09-14 | sprayed 4L Garlon(+/-60patches) along trail inside NATL, and on outside of fence in large patches.
2009-09-15 | spray1.5Lgarlon(+/-20patches)in woodsWof Trail/sprayed1.5L(+/-20patches)outside fence.**(Garlon w/ water+surfactant).
2009-09-30 | Garlon+oil worked very well, garlon+water is less effective.. Respray all water areas(~40) w/ Garlon+oil.
2009-10-12 | Little effect so far, waiting to see expected mortality to respray.
2009-11-02 | sprayed 4 new growths w/ 2% imazopyr. **(swithched to Imazopyr w/ water+surfactant).
2009-11-26 | none found.
2010-06-01 | none found.
2010-07-06 | none found.
2010-08-12 | small regrowth found on E side of fence in ditch.
AV3= | (temporary) NATL-e near GP O10 on E side of fence along water's edge
2009-11-02 | sprayed 2% imazopyr on S 1/5 (20%) of plants.
2009-11-26 | all plants seem viable; no effect from spraying.
2010-06-01 | died in winter/no regrowth found so far.
2010-07-06 | none found.
2010-08-12 | small regrowth found, not concern at this point… may need to be sprayed if get worse.

## Japanese climbing fern
NATL invasives: Japanese climbing fern (Lygodium japonicum)
JCF1= | north side of Gasline Trail, between G10 & H10
2007-07-17 | none found
2007-12-03 | sprayed glyphosate on 2 well-developed vines (1-3m in linear extent)
2008-07-07 | none found
2008-12-02 | none found
Divis.Trail= | north side of Divison Trail ca 90ft west of East Trail
2007-07-17 | 2 vines found and sprayed; the one farther from road had already been sprayed, by Kevin I assume
2007-12-03 | none found
2008-07-07 | none found
2008-12-02 | none found
East Trail= | on west edge of East Trail near its juncture with Division Trail in a spot where "air potato" had been sprayed
2006-09-06 | three vines discovered and sprayed with Prosecutor [=Lesco's glyphosate]
2007-07-17 | none found
2007-12-03 | none found
2008-07-07 | none found
2008-12-02 | none found
GaslineSV= | roadside of eastern extreme of south skunk-vine site
2006-10-01 | found and sprayed with Prosecutor 3 vigorous vines
2007-07-17 | none found
2007-12-03 | none found
2008-07-07 | none found
2008-12-02 | none found
Main Trail= | N side of Main Trail, just W of Pavilion
2009-05-09 | Found by interns, to be removed by roots
2010-06-02 | sprayed w/ Smith Formula (3.5gal H2O/9oz garlon4/2 tbsp Dyne-Amic)

## Mimosa
NATL invasives: Mimosa
Treated by Robert Guggenheim, starting in 2008.
2008-09-01 | cut and Garlon all of sRAP.
2009-10-12 | sprayed w/ garlon and oil (basel stem) along South Trail, Main Tr., DPI Tr., 34St. Tr.,East tr., Gaseline Tr.,
Division Tr., North tr., & RAP Firebreak.
2009-10-13 | Garlon all of sRAP & cut/Garlon W-half of nRAP to the C-gridline. Approx. ~30 large plants in E-half.
2009-11-02 | sprayed garlon on small plants near G12.
2009-11-04 | cut and sprayed garlon on rest of nRAP ~4hrs.

## Leucaena
NATL invasives: white leadtree (Leucaena leucophila)
Phillips= | southwest corner of Phillips Center rear parking lot and few stems on south side of fence in NATL
2007-12-12 | applied Garlon 4 basally to all stems (17 <5ft; 5>=5ft)
OF trail= | south end of Old-Field nature trail and source tree at start of Hammock trail (along Main Trail)
2007-12-12 | applied Garlon 4 basally to all stems (ca. 60, many more than 5ft); some from cut stems had grown from roots
Jul-08 | Ken Prestwich applied Garlon 4 to all stems he could find
Aug'08 | Ken Prestwich applied Garlon 4 to all stems he could find
2008-12-27 | applied Garlon 4 basally to all stems I could find (n=3; none more than 5 ft tall)
E7= | southwest corner of block E7 (ne corner of intersection of firelane and Division Trail)
2006-12-06 | applied Garlon 4 basally to stems of 2 or 3 small trees growing among the Vitex stems
2007-12-14 | applied Garlon 4 to one seedling tree growing among the dead Vitex stems

## Loquat
NATL invasives: Loquat or Japanese Plum
Treated by Robert Guggenheim, starting in 2009.
2009-10-12 | sprayed w/ garlon and oil (basel stem) along South Trail.
2009-11-02 | resprayed most plants w/ garlon, ~20.

## Paper Mulberry
NATL invasives: Paper Mulberry
Treated by Robert Guggenheim, starting in 2009.
2009-10-12 | sprayed w/ garlon and oil (basel stem) on larger trees along South Trail.
2009-11-02 | sprayed w/ garlon and oil (basel stem) on smaller trees around G12.

## Vitex
NATL invasives: negundo chastetree (Vitex negundo)
I5= | just north of Main Trail just east of pavilion
2006-12-06 | applied Garlon 4 basally to all stems in two well-separated clumps
summer 07 | Ken Prestwich applied Garlon 4 basally to stems that he noted
2007-12-14 | none found
E7= | southwest corner of block E7 (ne corner of intersection of firelane and Division Trail)
2006-11-29 | cut and applied Garlon 3A to the stumps of most stems (in single clump)
2006-12-06 | applied Garlon 4 basally to remaining stems
2007-12-14 | applied Garlon 4 basally to the one remaining live stem

## Lantana
NATL invasives: Lantana (Lantana camara)
NATL-e= | entrance to NATL-east
2007-12-03 | none found
2008 | none found

## Smilax in PAP
NATL invasives: Smilax
Treated by Robert Guggenheim, starting in 2010.
2010-05-24 | sprayed w/ Smith's Formula mix [3.5gal. H2O/ 9oz. Garlon 4/ 2tbsp. Dyne-Amic surfactant].
Along nPAP (marked 20 w/pink flags) & sPAP (double Garlon, marked 20 w/pink flags).
5450 plants sprayed in sPAP (completed).
2010-05-27 | sprayed 700 plants along west edge of nPAP, 10' in from edge.
2010-05-28 | sprayed 2350 plants east of UP Trail, starting at N- heading S to Grid Line 4.
2010-06-02 | sprayed another 900 plants S of Grid Line 4 on E-side of UP Trail.
Sprayed 20 plants with blue flags @ S-end of nPAP along Main Trail (W of UP Trail) w/ 1% imazapyr.
2010-06-03 | sprayed another 200 plants continuing S with Smith's Formula.
Also sprayed all of newly cleared area just W of Academic Pavilion (~6 gal).
2010-06-28 | Blue exp. In southern nPAP were all alive with minimal effect from spraying. Small brown spots on leaves.
Pink flags along W of nPAP & sPAP were > or = 90% dead, with no regrowth in exact location of flags.

## invasives summary07-09
Summary of Invasive Control 2007-2009
Kevin Ratkus and Tom Walker did the inspections and treatments in 2007;
Bob Guggenheim did them in 2008 and 2009
*Sum of maximum no. of patches treated
at each site during year
**Sum of all treatments of patches during year
Cogongrass
| Sites known to be infested |  |  | Severity of infestations and treatment effort
Year | Legacy sites | New sites | Total sites | Inspections | Treated patches* | Total treatments**
2007 | 35 | 1 | 36 | 4 | 892 | 1991
2008 | 24 | 3 | 27 | 3 | 911 | 1335
2009 | 24 | 2 | 26 | 4 | 1242 | 2206
| 17 Sep - 2 Dec 2009 |  | 24 | 3 | 964
| 20 Oct - 2 Dec 2009 |  | 19 | 2 | 584
Air Potato
| Sites known to be infested |  |  | Severity of infestations and treatment effort
Year | Legacy sites | New sites | Total sites | Inspections | Treated patches* | Total treatments**
2007 | 5 | 0 | 5 | 4 | 29 | 64
2008 | 3 | 1 | 4 | 6 | 124 | 256
2009 | 3 | 2 | 5 | 8 | 110 | 260
Skunkvine
| Sites known to be infested |  |  | Severity of infestations and treatment effort
Year | Legacy sites | New sites | Total sites | Inspections | Treated patches* | Total treatments**
2007 | 2 | 0 | 2 | 6 | 52 | 160
2008 | 2 | 0 | 2 | 7 | 125 | 270
2009 | 2 | 1*** | 3 | 7 | 95 | 115
***About 1000 m2 covered with skunkvine;
total treatments=42 (see below).
|  | Date | Patches treated
|  | 2009-08-25 | 1 (broadcast by sprayer truck)
|  | 2009-09-08 | 1 (broadcast by sprayer truck)
|  | 2009-10-12 | 38
|  | 2009-12-16 | 2
Arrowhead Vine
| Sites known to be infested |  |  | Severity of infestations and treatment effort
Year | Legacy sites | New sites | Total sites | Inspections | Treated patches* | Total treatments**
2007 | 1 | 1 | 2 | 1 | 63 | 63
2008 | 2 | 0 | 2 | 5 | 200 | 310
2009 | 2 | 1 | 3 | 5 | 244 | 514

## cat's claw vine
NATL invasives: cat's claw vine (Macfadyena unguis-cati)
sPAP= | on west side of east fire lane of sPAP, just south of gridstake E7
2006-10-12 | one infested tree trunk found (by Alison Fox)
2006-10-18 | sprayed vines with Prosecutor
2006-10-20 | sprayed vines with Prosecutor (because I was in the vicinity for air potato)
2007-06-30 | none found
2007-11-29 | none found
2008 | none found

## wandering Jew
NATL invasives: wandering Jew (Tradescantia zebrina )
2007-12-14 | Found none along South Trail opposite apartment complexes